## New Forest Lyndhurst
| Local Authority | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst | New Forest Lyndhurst
b. | Title of measure | Physical Traffic Management | Physical Traffic Management | Physical Traffic Management | Physical Traffic Management | Physical Traffic Management | Parking Management & Charging | Physical Traffic Management | Partnership & Travel Plans | Partnership & Travel Plans | Land Use Planning | Public Transport Initiatives - Bus | Development of Cycling and Walking | Parking Management & Charging | Fleet Management & clean fuels | Roadside Emissions Testing | Land Use Planning | Promotion, Education & Awareness Raising | Promotion, Education & Awareness Raising
c. | Summary taken from AQAP/ PR/LTP | Bypass. | Improvement of A337 / A35 junction. | Additional signalised junction on A35 / Shrubbs Hill Road. | Enforcement of HGV restriction. | Installation of variable messaging system. | Enforcement of parking restrictions. | Review signage in Lyndhurst. | Development of NFDC Travel Plan. | Development of school travel plan. | Planned developments. | Review bus routes. | Review cycle routes. | Review car parking. | Council fleet management. | Vehicle emissions testing. | Investigate use of absorbing paving surface. | Increase public awareness of air quality. | Review air quality monitoring.
d. | Has the measure been implemented? (Y/N) | N | N | N | Y | Y | N | Y (only 7.5t restriction) | Y | Y | Y | N | N | N | Y | N | N | Y | Y
e. | When was the measure first implemented? | n/a | n/a | n/a | Ongoing | 2008 | n/a | 2008 | Ongoing (started 2007) | Ongoing | Ongoing | n/a | n/a | n/a | 2007 | n/a | n/a | Ongoing | Ongonig
f. | Any updates on progress | Proposal taken through a County Council scrutiny review. Outcome - not supported at this time. | N | Modelling work undertaken by netcen using county traffic data to determine AQ improvements. Further work being undertaken. | Survey shows 11 vehicles in a 12hr period travelling illegally | Works during heavy traffic on A337 into Lyndhurst, but not as a priority scheme over other traffic messages. Need to assess against monitored AQ results. | Need to meet relevant officers | Further signage survey work required |  | Ongoing - to link with AQ work | Ongoing | N - limited due to rural location | Additional cycle parking in Lyndhurst | N | Ongoing - reviewed grey fleet and ecodriving measures in place | N | No longer an option | Information on website, further requirement to increase awareness | Ongoing
g. | Has the potential impact of the measure on emissions of NOx been quantified quantitatively? (Y/N) | N | N | Y | N | N | N | N | N | N | N | N | N | N | N | N | N | N | N
h. | If answer to (g.) is yes, please provide information here or attach a relevant reference document. | n/a | n/a | Work undertaken by netcen. Some AQ improvements - one scheme would reduce NO2 below objective, but not favourable with traffic flows. A new scheme currently being looked at for traffic and AQ feasibility. | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a | n/a
j. | Comments for clarification if needed
Reference(s)
Where the Council is aware of additional measures implemented that are not included in this form, please insert these in the columns to the right of the listed measures.