## info
pollutant | bap
time period | 2020
zones | Swansea | South Wales
zone codes | UK0027 | UK0041

## bap_swansea_southwales
inspireid localid | code | name | description | measure type | timescale | planned implementation | comment for clarification | completed | costs | reduction of emission | reduction of emission nil | reduction of emission nil reason | quantification numerical | comment | expected impact | changes | description of changes | reporting start date | reporting end date | status planned implementation | implementation planned time period begin position | implementation planned time period end position | planned full effect date | planned full effect date time position nil | monitoring progress indicators | monitoring progress indicators nil | monitoring progress indicators nil reason | planned implementation comment | estimated implementation costs | estimated implementation costs nil | estimated implementation costs nil reason | costs currency | costs comment | administraction level | classification | source sector | spatial scale | situation | attainment
K_natural_resources_wales_coke_ovens_1 | natural_resources_wales_coke_ovens_1 | New methods and Improvements | Measures to meet new fugitive BAT emission limits . BAT-Associated Emission Levels (BAT-AELs). BAT-Associated Emission Performance Levels (BAT-AEPLs) | intergrated | long | Implementation | Attainment as reported for 2020: GB_Attainment_183398;GB_Attainment_183412. Exceedance situation B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 as referred to in report on measures document (https://uk-air.defra.gov.uk/library/bap-nickel-measures). Additional information: TATA Steel has adopted a modified US EPA method for fugitive release assessment. This method uses a binary 'leak-no leak' assessment and directly compares to the BATc. TATA has previously committed to coke ovens life extension expenditure worth ~£3m/year over three years. The coke ovens life extension project is ongoing, and TATA continues to invest in this area. Compliance with the new limits has been summarised below for tops, doors and charging emissions. Where compliance has not been achieved, NRW has responded in accordance with its Compliance Classification Scheme (CCS) and has worked with TATA to achieve compliance with the BAT-AELs and AEPLs. NRW continues to apply CCS scores in response to any notifiable emission limit breaches. An EPR Regulation 61 Notice was used in 2018; TATA's response included an action plan with timescales outlining a pathway towards compliance. During 2020 the Notice and action plan remained active. NRW closed its Regulation 61 Notice in October 2021 as TATA had achieved the requirements. Compliance with the relevant emission limits (BAT-AEPLs) for coke oven doors, tops and charging emissions has been sustained since February 2019. MCO remains an important part of NRW's compliance inspection programme for Port Talbot steelworks and we continue to apply regulatory effort to ensure the permit requirements are met. Future work. Fugitive releases from Morfa Coke Ovens (MCO) are affected by the internal operating pressure of the ovens. This pressure is at its highest when ovens are initially charged with coal and there is the maximum production of coke oven gas (COG). The rate of COG production gradually decreases as the contents of the oven are carbonised. TATA has optimised the gas pressure controls on individual ovens to improve the overall control system and therefore minimise fugitive releases of B[a]P from its coke oven batteries. MCO's operational lifespan is projected to be the late-2020s thanks to the life extension project. As the coke oven batteries age, the likelihood of permit non-compliances and elevated emissions may increase despite the life extension measures. As MCO progresses towards the end of its extended campaign life, TATA should outline its strategy for this key asset and clarify its preferred method of iron and steelmaking going forwards. Other critical assets necessary for integrated iron and steelmaking (using Blast Furnace technology) are also approaching the end of their projected design life e.g. sinter plant. Replacement coke ovens may require significant planning (~5yrs design and construction) and capital expenditure (greater than £500m). Further notices will be considered by NRW if environmental performance deteriorates, and repeated CCS scores are incurred for emission limit breaches at MCO. |  |  |  | TRUE | Unpopulated | Tonne per year | Information not available |  | TRUE | Measures submitted for the first time for exceedances of the BaP target value in 2020. These measures are updates to measures submitted for excedances of the BaP target value in 2019: https://uk-air.defra.gov.uk/data/compliance-xml-files | 2020-01-01 | 2020-12-31 | Implementation | 2015-01-01 | 2027-12-31 | 2027-12-31 | FALSE | Emissions estimate | FALSE |  |  |  | TRUE | Unpopulated | GBP | Cost information not available from routinely collected data on local measures | Local | Measures to reduce pollution through permit systems and economic instruments | Industry including heat and power production | Local | B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 | GB_Attainment_183398;GB_Attainment_183412
K_natural_resources_wales_coke_ovens_2 | natural_resources_wales_coke_ovens_2 | Spigot improvements | Spigot improvements. The spigot is the joint between the oven and the gas main. Measures include fitting of new collars, 'repacking' existing spigot seals, fitting new seals and, shortening of ascension pipes. | intergrated | long | Implementation | Attainment as reported for 2020: GB_Attainment_183398;GB_Attainment_183412. Exceedance situation B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 as referred to in report on measures document (https://uk-air.defra.gov.uk/library/bap-nickel-measures). Additional information: Control of fugitive emissions from coke ovens will result in lower B[a]P emissions. The BAT-AEPL (Associated Emission Performance Level) for coke oven tops is 1% leakage rate (99% leak free). A sequential programme of work has been ongoing to progressively reduce leakage. This has been balanced against the complexities of working on live coke oven batteries (ovens are kept in continuous operation). Significant effort has been applied by TATA to reduce fugitive emissions from coke oven tops. Improved performance has coincided with secured capital expenditure (coke ovens life extension project) and an optimised maintenance regime involving rolling replacement of ascension pipes and repair/re-sealing of spigots. TATA has also overhauled its COG collector main control systems and renewed its gas pressure monitoring capability, allowing faster response to COG pressure imbalances and greater protection for spigot components. NRW has responded to any identified permit non-compliance in accordance with its Compliance Classification Scheme (CCS). NRW's response to identified non-compliance has included the use of an EPR Regulation 61 Notice (see Measure Code 1 above). Significant progress has been made with 99% leak free performance achieved in February 2019. Compliance with the BAT-AEPL for tops has since been sustained over many months. Target achieved (less than 1% leakage) but ongoing maintenance is necessary to sustain compliance. Coke Ovens performance is discussed at least every quarter with Tata Steel. Sustained compliance may become more challenging as the batteries approach the end of their campaign life. Future work. It should be noted that as the ovens age, the likelihood of permit non-compliances and elevated emissions may increase despite the life extension measures. At Morfa Coke Ovens (MCO) there are two COG collection mains for each oven and four charge holes. TATA has completed a feasibility study for converting MCO to a single COG collection main. A single main would significantly reduce the number of emission points along the coke oven battery tops; however, TATA's feasibility study and cost-benefit analysis does not support a viable single COG main conversion. The overhauled and renewed COG pressure control systems at MCO should – with sufficient maintenance – allow effective control of emissions from coke oven tops. This work has been combined with control improvements at the MCO Exhauster unit which draws COG from the coke oven batteries. TATA has trialled mechanical spigots on some ovens but has concluded that its current programme of prioritising and (manually) repairing/re-sealing spigot joints is sufficient to maintain performance. More generally, TATA should outline its future strategy for MCO and clarify its preferred method of iron and steelmaking going forwards, within a wider context of developing low-carbon steelmaking technology. |  |  |  | TRUE | Unpopulated | Tonne per year | Information not available |  | TRUE | Measures submitted for the first time for exceedances of the BaP target value in 2020. These measures are updates to measures submitted for excedances of the BaP target value in 2019: https://uk-air.defra.gov.uk/data/compliance-xml-files | 2020-01-01 | 2020-12-31 | Implementation | 2015-01-01 | 2019-12-31 | 2019-12-31 | FALSE | Percentage leak rate reduced to target of 1% | FALSE |  |  |  | TRUE | Unpopulated | GBP | Cost information not available from routinely collected data on local measures | Local | Measures to reduce pollution through permit systems and economic instruments | Industry including heat and power production | Local | B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 | GB_Attainment_183398;GB_Attainment_183412
K_natural_resources_wales_coke_ovens_3 | natural_resources_wales_coke_ovens_3 | Coke Oven door improvements | Coke Oven door improvements. Each coke oven has two sets of doors at either end. Hot coke is pushed from the 'ram side' doors through the 'coke side' doors into waiting rail cars. Doors and door frames require regular maintenance and periodic replacement to minimise fugitive emissions. | intergrated | long | Implementation | Attainment as reported for 2020: GB_Attainment_183398;GB_Attainment_183412. Exceedance situation B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 as referred to in report on measures document (https://uk-air.defra.gov.uk/library/bap-nickel-measures). Additional information: Control of fugitive emissions from coke ovens will result in lower B[a]P emissions. The BAT-AEPL (Associated Emission Performance Level) for coke oven doors is 10% leakage rate (90% leak free). A sequential programme of work has progressively reduced door leakage. This has been balanced against the complexities of working on live coke oven batteries (ovens are kept in continuous operation). An optimised coke oven door cleaning, maintenance and repair programme is in place at MCO. TATA has standardised its door cleaning methods and invested in new jetting equipment. TATA also periodically replaces degraded doors and door seals. The door leakage rate has dropped noticeably across both batteries. Improved performance has coincided with secured capital expenditure (coke ovens life extension project) and refinement of maintenance plans and procedures. NRW has responded to any identified permit non-compliance in accordance with its Compliance Classification Scheme (CCS). NRW's response to identified non-compliance has included the use of an EPR Regulation 61 Notice (see Measure Code 1 above). Significant progress has been made with 90% leak free performance achieved in August 2018. Compliance with the BAT-AEPL for doors has since been sustained over many months. Target achieved (less than 10% leakage) but ongoing maintenance is necessary to sustain compliance. Coke Ovens performance is discussed at least every quarter with Tata Steel. Sustained compliance may become more challenging as the batteries approach the end of their campaign life. Future work: . It should be noted that as the ovens age, the likelihood of permit non-compliances and elevated emissions may increase despite the life extension measures. Leaks from coke oven doors occur when hot gases penetrate the seals between the door and its frame. Doors and frames are routinely cleaned to ensure a tight seal. At MCO, a 'knife-edge' door seal design is employed. Previously TATA considered a remotely controlled cleaning device for the small 'leveller' doors which are difficult to clean. This has been abandoned for technical reasons. TATA's door cleaning programme targets leveller doors and seals to provide equivalent cleaning. TATA has trialled a new type of coke oven door (with tighter 'z' seals). However, increased cleaning efficiency, improved knife-edge seal design and optimised maintenance has resulted in better door sealing. Door frame cleaning functionality also exists on MCO's ram and guide machines. The scope of TATA's door trial has evolved and is now part of its continuous improvement initiatives at MCO. The Original Equipment Manufacturer (OEM) is examining the existing door design to minimise and potentially eliminate manual intervention. More generally, TATA should outline its future strategy for MCO and clarify its preferred method of iron and steelmaking going forwards, within a wider context of developing low-carbon steelmaking technology. |  |  |  | TRUE | Unpopulated | Tonne per year | Information not available |  | TRUE | Measures submitted for the first time for exceedances of the BaP target value in 2020. These measures are updates to measures submitted for excedances of the BaP target value in 2019: https://uk-air.defra.gov.uk/data/compliance-xml-files | 2020-01-01 | 2020-12-31 | Implementation | 2015-01-01 | 2019-12-31 | 2019-12-31 | FALSE | Percentage leak rate reduced to target of 10% | FALSE |  |  |  | TRUE | Unpopulated | GBP | Cost information not available from routinely collected data on local measures | Local | Measures to reduce pollution through permit systems and economic instruments | Industry including heat and power production | Local | B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 | GB_Attainment_183398;GB_Attainment_183412
K_natural_resources_wales_coke_ovens_4 | natural_resources_wales_coke_ovens_4 | Reduction of emissions during charging | Reduction of emissions during charging. Coke ovens are 'charged' with coal through charge holes in the top of each oven. The charging nozzles, holes and lids all require regular maintenance and periodic replacement to minimise fugitive emissions. . . | intergrated | long | Implementation | Attainment as reported for 2020: GB_Attainment_183398;GB_Attainment_183412. Exceedance situation B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 as referred to in report on measures document (https://uk-air.defra.gov.uk/library/bap-nickel-measures). Additional information: Control of fugitive emissions from coke ovens will result in lower B[a]P emissions. BAT-AEPL for visible emissions from charging is less than 30 seconds per charge expressed as a monthly mean. A sequential programme of work has progressively reduced charging emissions. This has been balanced against the complexities of working on live coke oven batteries (ovens are kept in continuous operation). Key items of equipment (charge holes and the coal charging apparatus) have now all been refurbished and/or replaced. Charging emissions have dropped noticeably across both batteries, often achieving around 20 seconds visible emissions per charge as a monthly average. Improved performance has coincided with secured capital expenditure (coke ovens life extension project) and refinement of maintenance plans and procedures. NRW has responded to any identified permit non-compliance in accordance with its Compliance Classification Scheme (CCS). NRW's response to identified non-compliance has included the use of an EPR Regulation 61 Notice (see Measure Code 1 above). Significant progress has been made and charging emissions have been compliant with the BAT-AEPL since February 2019. Compliance has since been sustained over many months. Target achieved (less than 30 seconds visible emissions per charge) but ongoing maintenance is necessary to sustain compliance. Target achieved (less than 30 seconds visible emissions per charge) but ongoing maintenance is necessary to sustain compliance. Coke Ovens performance is discussed at least every quarter with Tata Steel. Sustained compliance may become more challenging as the batteries approach the end of their campaign life. Future work. It should be noted that as the ovens age, the likelihood of permit non-compliances and elevated emissions may increase despite the life extension measures. TATA continues to follow a rolling maintenance programme for its coke oven charging equipment. This includes surveying charge holes and correcting mis-aligned charge hole frames. Automatic systems to seal charge hole lids and clean carbon residues from holes and frames have been considered with technical input from the Original Equipment Manufacturer (OEM). TATA has determined that its current programme of manual sealing and cleaning provides an equivalent level of performance. TATA has indicated that it will retain a dedicated resource going forwards for charge hole lid sealing and carbon cleaning. More generally, TATA should outline its future strategy for MCO and clarify its preferred method of iron and steelmaking going forwards, within a wider context of developing low-carbon steelmaking technology. |  |  |  | TRUE | Unpopulated | Tonne per year | Information not available |  | TRUE | Measures submitted for the first time for exceedances of the BaP target value in 2020. These measures are updates to measures submitted for excedances of the BaP target value in 2019: https://uk-air.defra.gov.uk/data/compliance-xml-files | 2020-01-01 | 2020-12-31 | Implementation | 2015-01-01 | 2958465 | 2958465 | FALSE | Duration of release reduced to 30 seconds as a monthly mean | FALSE |  |  |  | TRUE | Unpopulated | GBP | Cost information not available from routinely collected data on local measures | Local | Measures to reduce pollution through permit systems and economic instruments | Industry including heat and power production | Local | B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 | GB_Attainment_183398;GB_Attainment_183412
K_natural_resources_wales_coke_ovens_5 | natural_resources_wales_coke_ovens_5 | Reduction of emissions during coke pushing | Reduction of emissions during coke pushing. Finished coke is pushed from each oven into specially designed rail cars. A mobile fume extraction system (also known as a coke-side arrestment system) is used at Port Talbot to capture fugitive emissions from coke pushing. | intergrated | long | Implementation | Attainment as reported for 2020: GB_Attainment_183398;GB_Attainment_183412. Exceedance situation B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 as referred to in report on measures document (https://uk-air.defra.gov.uk/library/bap-nickel-measures). Additional information: Control of fugitive emissions from coke ovens will result in lower B[a]P emissions. The BAT-AEL for coke pushing (dust) emissions is 10mg/m3 for bag filters and 20mg/m3 in all other cases, measured using discontinuous monitoring (spot sampling). A venturi scrubber system is used at Port Talbot; therefore, the applicable emission limit is 20mg/m3. This has been reflected in TATA's permit since 2015 (no change). There have been no verified breaches of the BAT-AEL since it came into force. Oven heating issues can result in poorly carbonised batches of coke. When pushed, visible emissions increase ('black pushes') and can overwhelm the fume extraction system. Availability of the guide car and fume extraction system can also influence fugitive emission levels. MCO's original system dated from the 1980s and has suffered reliability issues. The system has since been refurbished and now comprises a replacement hood, extraction system, guide car and ducting. The new system has enhanced fume capture capability. Water sprays have been used during the period of unavailability to 'knock down' fugitive emissions from coke pushing. There is a rolling programme of repair and refurbishment for the oven gas (heating) flues. Coke oven temperature profiles and coke yields are positively affected by keeping as many gas flues as possible in working order. The difficulty associated with this work increases as the batteries age. NRW has introduced a reporting metric for the number of black pushes at the coke ovens. This data is now reported quarterly and is harmonised with other similar reporting requirements. Target achieved (20mg/m3 for particulates) but ongoing maintenance is necessary to sustain compliance. Black pushes are scrutinised using new performance metric (see above). Coke Ovens performance is discussed at least every quarter with Tata Steel. Sustained compliance may become more challenging as the batteries approach the end of their campaign life. Future work. Discontinuous sampling has been retained for monitored emissions from coke pushing. TATA has progressed its repair programme for coke oven flues and regenerators. This work involves targeting ovens with damaged/degraded flues and regenerators, but also developing a better understanding of how this influences black push emissions. Some oven walls (with embedded flues) are also being repaired. TATA's capital expenditure (coke ovens life extension project) is allowing delivery of this work. Refurbished and enhanced coke-side fume arrestment system is now fully commissioned and online as of July 2021. Project delivery has been impacted by factors such as delayed crane lifts (bad weather) and Covid-19 business disruption. Black push numbers are being monitored by NRW to assess if TATA's interventions are having a positive influence on environmental performance. More generally, TATA should outline its future strategy for MCO and clarify its preferred method of iron and steelmaking going forwards, within a wider context of developing low-carbon steelmaking technology. |  |  |  | TRUE | Unpopulated | Tonne per year | Information not available |  | TRUE | Measures submitted for the first time for exceedances of the BaP target value in 2020. These measures are updates to measures submitted for excedances of the BaP target value in 2019: https://uk-air.defra.gov.uk/data/compliance-xml-files | 2020-01-01 | 2020-12-31 | Implementation | 2015-01-01 | 2020-12-31 | 2020-12-31 | FALSE | Compliance with 20 mg/m3 BAT-AEL. Reduced numbers of black pushes | FALSE |  |  |  | TRUE | Unpopulated | GBP | Cost information not available from routinely collected data on local measures | Local | Measures to reduce pollution through permit systems and economic instruments | Industry including heat and power production | Local | B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 | GB_Attainment_183398;GB_Attainment_183412
K_natural_resources_wales_sinter_plant | natural_resources_wales_sinter_plant | Improvements to operations | Improvements to Lignite Injection. Lignite is used in combination with lime to trap and neutralise certain pollutants present in hot flue gases. These additives are injected directly into the hot flue gases. The integrity of the flues and the emissions abatement systems must be sound for lignite-lime injection to be used safely. . . | intergrated | long | Implementation | Attainment as reported for 2020: GB_Attainment_183398;GB_Attainment_183412. Exceedance situation B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 as referred to in report on measures document (https://uk-air.defra.gov.uk/library/bap-nickel-measures). Additional information: Lignite-lime injection forms part of several projects to ensure that the sinter plant complies with tighter EU (IED) standards. There are no specific BATc or BAT-AELs designed to reduce B[a]P from sinter plant emissions. However, reducing overall emissions will result in lower B[a]P emissions. Associated work and regulatory interventions by NRW to address persistent particulate emission limit (BAT-AEL) breaches from the sinter plant main stack should indirectly reduce B[a]P emissions from this source. Main stack particulate emissions: TATA responded to an EPR Regulation 61 Information Notice in August 2018. The company's response included an action plan with timescales outlining a pathway towards compliance. The notice currently remains open. The lignite-lime injection system at Port Talbot has not yet been commissioned. To allow use of this technology at the sinter plant, some important preparatory steps must be completed first: Air ingress issues within the main stack waste gas system must be resolved. A key performance indicator is 17% oxygen within the waste gas stream - sensors are now in place to monitor this. Upgraded valves at the base of each ESP (dust) collection hopper are subject to a rolling maintenance programme. Previously the valve seals were degrading too quickly and allowing air into the system. Sinter process instability has contributed to elevated stack emissions and degraded ESP performance. TATA has several ongoing projects to address process instability. TATA continues to pursue these steps at the time of writing. Bringing lignite-lime online prematurely can result in fires starting within the main stack Electrostatic Precipitators (ESPs) as a result of lignite (fuel) + heat + oxygen. The Sinter Plant remains an important part of NRW's compliance inspection programme for Port Talbot steelworks and we continue to apply regulatory effort to ensure the permit requirements are met. Future work. Several factors have delayed the implementation of the lignite-lime injection scheme. This includes (but is not limited to) Covid-19 disruption and EU Exit impact. The interior of each ESP and the (waste gas) wind main system are subject to high temperatures and continual physical abrasion by entrained dust, which progressively wears away exposed surfaces and parts. Keeping pace with this degradation and maintaining an 'air-tight' system is critical to the safe commissioning of lignite-lime injection. Tata Steel has adjusted its maintenance strategy to allow shorter stops to be taken more frequently within a quarterly maintenance framework, enabling worn parts to be replaced before they degrade completely. The engineering challenges and associated unavailability of lignite-lime injection may increase as the sinter plant ages. Tata continues to explore a contingency solely involving the use of lime products i.e. no lignite. There are customised lime compounds available that may deliver similar levels of waste gas reagent performance and are also capable of removing micro-pollutants. These compounds present a much lower risk of combustion compared to lignite and the impact of air (O2) ingress becomes less pronounced. Use of customised lime products as waste gas reagents is Tata's contingency plan should the air ingress issues prove insurmountable. The lignite-lime system is unlikely to be commissioned until the preparatory works outlined in this table have been completed and TATA's senior management authorise the scheme. No timescale has been agreed with NRW yet. As the Sinter Plant ages, TATA should outline its strategy for this key asset and clarify its preferred method of iron and steelmaking going forwards. A replacement sinter plant (incorporating lignite-lime injection) may require significant planning and capital expenditure. Other critical assets necessary for integrated iron and steelmaking (Blast Furnace technology) are also ageing e.g. Morfa Coke Ovens. TATA should present its strategy within a wider context of developing low-carbon steelmaking technology.The system is unlikely to be commissioned until the preparatory works outlined in this table have been completed and TATA's senior management authorise the scheme. As the Sinter Plant ages, TATA should outline its strategy for this key asset and clarify its preferred method of iron and steelmaking going forwards. Other critical assets necessary for integrated iron and steelmaking (using Blast Furnace technology) are also ageing e.g. Morfa Coke Ovens. TATA should present its strategy within a wider context of developing low-carbon steelmaking technology. A replacement sinter plant may require significant planning and capital expenditure. |  |  |  | TRUE | Unpopulated | Tonne per year | Information not available |  | TRUE | Measures submitted for the first time for exceedances of the BaP target value in 2020. These measures are updates to measures submitted for excedances of the BaP target value in 2019: https://uk-air.defra.gov.uk/data/compliance-xml-files | 2020-01-01 | 2020-12-31 | Implementation | 2015-01-01 | 2025-12-31 | 2025-12-31 | FALSE | We expect the monitored B[a]P results in Port Talbot to start to drop in 2016. | FALSE |  |  |  | TRUE | Unpopulated | GBP | Cost information not available from routinely collected data on local measures | Local | Measures to reduce pollution through permit systems and economic instruments | Industry including heat and power production | Local | B[a]P_UK0027_2020_1;B[a]P_UK0041_2020_1 | GB_Attainment_183398;GB_Attainment_183412

## option_lists
measure type | timescale | planned implementation | reduction of emission nil | quantification numerical | changes | status planned implementation | monitoring progress indicators nil | estimated implementation costs nil | costs currency | administrative level | classification | source sectors | spatical scale
coordinated | long | Annulation | TRUE | kilotonne per year | TRUE | Annulation | TRUE | TRUE | BGN | Local | Emission control equipment for small and medium sized stationary combustion sources / replacement of combustion sources | Agriculture | Local
integrated | medium | Evaluation | FALSE | Tonne per kilometer per year | FALSE | Evaluation | FALSE | FALSE | CHF | National | Low emission fuels for small, medium and large scale stationary sources and in mobile sources | Commercial and residential sources | National
other | short | Implementation |  | Tonne per square kilometer per year |  | Implementation |  |  | CZK | Regional | Measures to reduce pollution through permit systems and economic instruments | Industry including heat and power production | Town as part of a zone
outside | unknown | Other |  | Tonne per year |  | Other |  |  | DKK |  | Other measure | Off-road machinery | Zone / Agglomeration
sensitive |  | Planning |  |  |  | Planning |  |  | EUR |  | Public procurement | Other, please specify
short |  | Preparation |  |  |  | Preparation |  |  | GBP |  | Public information/Education via leaflets | Shipping
[9 empty] | GIP |  | Public information/Education via other mechanisms | Transport
[9 empty] | HRK |  | Public information/Education via radio.
[9 empty] | HUF |  | Public information/Education via television
[9 empty] | ISK |  | Retrofitting emission control equipment to vehicles
[9 empty] | NOK |  | Traffic planning and management
PLN
RON
RSD
SEK
TRY